## Sheet1
Task Name | Start Date | End Date | Duration | Assigned To | Progress | Sprint | Notes
Project Kickoff Meeting | 2025-01-06 | 2025-01-07 | 2 | Project Manager | 0 | Sprint 0 | Kickoff meeting with stakeholders
Requirement Gathering | 2025-01-08 | 2025-01-17 | 10 | BA Team | 0 | Sprint 0 | Workshops and documentation
Sprint Planning - Sprint 1 | 2025-01-08 | 2025-01-08 | 1 | Scrum Master | 100 | Sprint 1
Develop Login Feature | 2025-01-09 | 2025-01-16 | 8 | Dev Team A | 80 | Sprint 1
Develop Signup Feature | 2025-01-09 | 2025-01-16 | 8 | Dev Team A | 70 | Sprint 1
QA Testing - Login/Signup | 2025-01-17 | 2025-01-20 | 4 | QA Team | 0 | Sprint 1
Sprint Review - Sprint 1 | 2025-01-21 | 2025-01-21 | 1 | Scrum Master | 0 | Sprint 1
Sprint Retrospective - Sprint 1 | 2025-01-22 | 2025-01-22 | 1 | Scrum Master | 0 | Sprint 1
Fix Critical Bug in Signup | 2025-01-23 | 2025-01-24 | 2 | Dev Team A | 0 | Sprint 2
Sprint Planning - Sprint 2 | 2025-01-18 | 2025-01-19 | 2 | Scrum Master | 0 | Sprint 2 | Plan Invoice Upload and OCR tasks
Invoice Upload + Duplicate Check | 2025-01-20 | 2025-01-27 | 8 | Dev Team | 0 | Sprint 2
OCR Extraction + DataFrame Creation | 2025-01-28 | 2025-02-04 | 8 | Dev Team | 0 | Sprint 2
Sprint Review - Sprint 2 | 2025-02-05 | 2025-02-05 | 1 | Scrum Master | 0 | Sprint 2 | Milestone
Sprint Retrospective - Sprint 2 | 2025-02-06 | 2025-02-06 | 1 | Scrum Master | 0 | Sprint 2 | Milestone
Sprint Planning - Sprint 3 | 2025-02-07 | 2025-02-08 | 2 | Scrum Master | 0 | Sprint 3 | Plan Display and Filtering
Display & Filter Invoices by Date/Month | 2025-02-09 | 2025-02-16 | 8 | Dev Team | 0 | Sprint 3
Invoice View + Modal Split Button | 2025-02-17 | 2025-02-24 | 8 | Dev Team | 0 | Sprint 3
Sprint Review - Sprint 3 | 2025-02-25 | 2025-02-25 | 1 | Scrum Master | 0 | Sprint 3 | Milestone
Sprint Retrospective - Sprint 3 | 2025-02-26 | 2025-02-26 | 1 | Scrum Master | 0 | Sprint 3 | Milestone
Sprint Planning - Sprint 3.5 | 2025-02-27 | 2025-02-27 | 1 | Scrum Master | 0 | Sprint 3.5 | Plan Admin Dashboard
Admin: Promote/Demote/Delete User | 2025-02-28 | 2025-03-07 | 8 | Dev Team | 0 | Sprint 3.5
Admin: View Settlement Summary | 2025-03-08 | 2025-03-15 | 8 | Dev Team | 0 | Sprint 3.5
Sprint Review - Sprint 3.5 | 2025-03-16 | 2025-03-16 | 1 | Scrum Master | 0 | Sprint 3.5 | Milestone
Sprint Retrospective - Sprint 3.5 | 2025-03-17 | 2025-03-17 | 1 | Scrum Master | 0 | Sprint 3.5 | Milestone
Sprint Planning - Sprint 4 | 2025-03-18 | 2025-03-19 | 2 | Scrum Master | 0 | Sprint 4 | Plan Splitting and Balances
Split Invoice Functionality | 2025-03-20 | 2025-03-27 | 8 | Dev Team | 0 | Sprint 4
Balance Calculation View + Settlements | 2025-03-28 | 2025-04-04 | 8 | Dev Team | 0 | Sprint 4
Settlement Logging/Partial Payments | 2025-04-05 | 2025-04-10 | 6 | Dev Team | 0 | Sprint 4
Sprint Review - Sprint 4 | 2025-04-11 | 2025-04-11 | 1 | Scrum Master | 0 | Sprint 4 | Milestone
Sprint Retrospective - Sprint 4 | 2025-04-12 | 2025-04-12 | 1 | Scrum Master | 0 | Sprint 4 | Milestone
UI/UX Polish: Modals, Buttons, Toasts | 2025-04-13 | 2025-05-02 | 20 | UI Team | 0 | Styling & UI | Ongoing during sprints
Sprint Planning - Sprint 5 | 2025-05-03 | 2025-05-04 | 2 | Scrum Master | 0 | Sprint 5 | Plan QA & Testing
Unit Tests for OCR, Splitting, Login | 2025-05-05 | 2025-05-12 | 8 | QA Team | 0 | Sprint 5
Manual QA: PDF Uploads, Admin, Edge Cases | 2025-05-13 | 2025-05-20 | 8 | QA Team | 0 | Sprint 5
Sprint Review - Sprint 5 | 2025-05-21 | 2025-05-21 | 1 | Scrum Master | 0 | Sprint 5 | Milestone
Sprint Retrospective - Sprint 5 | 2025-05-22 | 2025-05-22 | 1 | Scrum Master | 0 | Sprint 5 | Milestone
Sprint Planning - Sprint 6 | 2025-05-23 | 2025-05-24 | 2 | Scrum Master | 0 | Sprint 6 | Plan Deployment
Deployment | 2025-05-25 | 2025-05-31 | 7 | DevOps Team | 0 | Sprint 6
Final Report & Submission | 2025-06-01 | 2025-06-05 | 5 | Project Manager | 0 | Sprint 6
Buffer Time | 2025-06-06 | 2025-06-15 | 10 | All Teams | 0 | Sprint 6 | Catch-up or issues fixing
Sprint Review - Sprint 6 | 2025-06-16 | 2025-06-16 | 1 | Scrum Master | 0 | Sprint 6 | Milestone
Sprint Retrospective - Sprint 6 | 2025-06-17 | 2025-06-17 | 1 | Scrum Master | 0 | Sprint 6 | Milestone